## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
Implementation
TASKS
task.c | ahmed &hossam &alaa | Done | 3 | 8
button 1 | khaled | Done | 1 | 1
button2 | khaled | Done | 1 | 1
perodic transmitter | khaled | Done | 1 | 1
uart_receiver | sarah | Done | 2 | 1
load1 simulator | sarah | Done | 1 | 1
load 2 simulator | sarah | Done | 1 | 1
system calculation | ahmed &hossam &alaa | Done | 3 | 4
Testing
Documentation
pdf | ahmed &hossam &alaa | Done | 4 | 3
backlog | sarah | Done | 1 | 0.5
System Testing
Test APP |  | Done | 1 | 1
Final Requirements Review |  | Done | 1 | 0.5
Video
Video Recording | All Team | Pending | 1 | 1
video 3 min | sarah | Pending